## Sheet1
Risk | Description | Prob. Of Occurence | Damage | Mitigation Strategy | Person in Charge | Risk Faktor
Landscape Migration | New Servers for PM as well as for development/deployment aren’t working in time | medium | high | Backup strategy, switch back to old hosting solution, that already worked | Philipp | high
Time delay | Time delay with the tasks assigned to a person within one sprint | high | medium | Rebalance work load between team members, at least after the week on the next sprint meeting | Florian | medium
Disagreement | not aligned on topics/features/implementations | medium | medium | Open discussion, realignment, democratic choice out of three | Florian | medium
Underestimation of complexity | Task that take longer than expected, dispite rebalancing accross the whole team | low | high | redefine scope | Lukas | medium
Sickness | Any one of us gets ill and that way isn’t able to work | low | medium | Know each others code well, worstcase redefine scope | Lukas | low
Data loss | Due to a PC crash or similar things before git pushes | low | low | Accurate git version control usage | Philipp | low